## Team Structure
Group 6
No. | Members | Note
1 | Duc Phuoc Doan | All memvers join to design, coding, integration and testing. Details is in WBS sheet
2 | Duy Thai Nguyen
3 | Yohannes Teweldeberhan
4 | Biniam Tsehaye Arefaine
5 | Tesfai Habtai Samuel

## WBS
WBS - Team 6
No. | Task | Description | PIC | Status
1 | Project framework: common framework for 2 application, then put in Github | - Create project structure, framework for starting the implementation - Update framework during implementation - Apply Singleton pattern for AcountDAO | Duc Phuoc Doan | Done
2 | Class Diagram | - The first draft for team discussion - Update from team disucssion - Maintain during changes in implementation | Duy Thai Nguyen | Done
3 | Personal Account -> Deposit/Withdraw/Calculate Interest | To implement full flow from DB to UI, apply Strategy Pattern and Observer pattern these functions: - Create Personal Account - Deposit and Withdraw - Calculate interests For each the fuction, we need to do: - Review Class diagram - Implementation - Sequence Diagram | Duy Thai Nguyen | Done
4 | Company Account -> Calculate Interest | To implement full flow from DB to UI, apply Strategy Pattern and Observer pattern these functions: - Create Company Account - Deposit and Withdraw - Calculate interests For each the fuction, we need to do: - Review Class diagram - Implementation - Sequence Diagram | Duy Thai Nguyen | Done
5 | Generate Billing report of Credit Card application | Report for the part 2, Billing report - Review Class diagram - Implementation - Sequence Diagram | Duc Phuoc Doan | Done
6 | Generate Report of Banking application | Report for the part 1, Bank Statement - Review Class diagram - Implementation - Sequence Diagram | Yohannes Teweldeberhan. | Done
7 | Create Credit Card -> Deposit Account | Full flow from DB to UI, and Observer pattern: - Create CreditCard - Deposit and Charge For each feature, we do below tasks: - Review Class diagram - Implementation - Sequence Diagram | Biniam Tsehaye Arefaine | Done
8 | Charge Account | Full flow from DB to UI, and Observer pattern: - Create CreditCard - Deposit and Charge For each feature, we do below tasks: - Review Class diagram - Implementation - Sequence Diagram | Tesfai Habtai Samuel | Done
9 | Integration and Testing | Integrate the whole system and do testing | All | Done

## Data Test
No. | Checking/Saving | AccountNo | Name | Street | City | State | Zip | Num | Email | Deposit | Withdraw | Interest |  | Total | Interest
| Checking | C001-0001 | C001-0001 | N 1st | Fairfield | IA | 52557 | 5 | ndt.rachkien@gmail.com | 10000 | 100 | 3465 | 0.7 | 13365 | 4677.75
| Checking | C001-0002 | C001-0002 | N 2nd | Fairfield | IA | 52557 | 5 | ndt.rachkien@gmail.com | 400 | 500 | 140 | 0.35 | 40 | 14
| Saving | C001-0003 | C001-0003 | N 3rd | Fairfield | IA | 52557 | 5 | ndt.rachkien@gmail.com | 20000 | 800 | 13440 |  | 32640 | 22848
| Saving | C001-0004 | C001-0004 | N 4th | Fairfield | IA | 52557 | 5 | ndt.rachkien@gmail.com | 500 | 100 | 280 |  | 680 | 476
Personal Account | [13 empty] | 0
| Checking | P001-1001 | P001-1001 | N 1st | Fairfield | IA | 52557 | 1960-01-01 | ndt.rachkien@gmail.com | 1000 | 10 | 247.5 | 0.6 | 1237.5 | 309.375
| Checking | P001-1002 | P001-1002 | N 2nd | Fairfield | IA | 52557 | 1960-01-01 | ndt.rachkien@gmail.com | 40 | 50 | 10 | 0.25 | 50 | 12.5
| Saving | P001-1003 | P001-1003 | N 3rd | Fairfield | IA | 52557 | 1960-01-01 | ndt.rachkien@gmail.com | 200 | 80 | 72 |  | 192 | 115.2
| Saving | P001-1004 | P001-1004 | N 4th | Fairfield | IA | 52557 | 1960-01-01 | ndt.rachkien@gmail.com | 50 | 10 | 24 |  | 64 | 38.4